## Sheet1
ISSUES LIST - as of 7/22/2026 (Use CTRL-F to search on keyword. Closed issues remain on list shaded in gray.)
Number | Provider Type | Category | Issue | Status | Resolution |  | Date Resolved
1 | Institutional | Claims | Claims have not been processed against the Grouper updates made in Fall of 2013 | Closed | Reprocessing of claims for Grouper 31 were in the April 8 checkwrite and reprocessing of claims (filed after July 1 2013) for Grouper 30 were in the April 22 checkwrite. Reprocessing of claims for the remaining Grouper updates was completed in the June 24 checkwrite.
2 | All | Claims | Medicare-only modifiers not recognized by NCTracks are causing crossover claims to deny | Closed | This issue was resolved on June 8. Providers will need to refile the denied claims. Note that this change affects modifiers used by Medicare only, which will now be allowed in NCTracks on crossover claims. It does not affect modifiers used for Medicaid Fee for Service processing, for which existing business rules still apply. |  | 2014-06-08
3 | All | Enrollment | Providers periodically receiving error when accessing or submitting a MCR indicating "Unable to Retrieve/Submit Manage Change Request Application." Seems to affect providers who have multiple NPIs listed under one NCID | Closed | The MCR process was updated on August 2 2015. Monitoring to determine if problem is resolved. See issue #127 for follow-up. |  | 2015-11-11
4 | All | Remittance Advice | When a recipient number is not in NCTracks, a default name was used for that recipient on the Remittance Advice | Closed | This issue was resolved on April 19 |  | 2014-04-19
5 | Private Duty Nursing & Behavioral Health | Claims | Private Duty Nursing claims not matching to their corresponding Prior Approvals due to a modifier issue. Also affected some Behavioral Health claims. | Closed | This issue was resolved on March 9. Providers need to resubmit claims. |  | 2014-03-09
6 | Professional | Claims | When a provider enters claim information in the NCTracks portal, the NDC information is not retained and the claim is denied. | Closed | This issue was resolved on January 19. If any providers are still having issues with the NDC not transmitting, they need to update their Java and resubmit the claim. |  | 2015-01-19
7 | All | Eligibility | The Patient Monthly Liability information on recipient eligibility records in NCTracks is missing or incorrect. | Ongoing | Time required for synchronization has been reduced and we are continuing to work with NCFAST. In the meantime, providers can ask the NCTracks Call Center to check eligibility in NCFAST.
8 | All | Eligibility | Newly enrolled Medicaid recipients are missing from NCTracks | Ongoing | Time required for synchronization has been reduced and we are continuing to work with NCFAST. In the meantime, providers can ask the NCTracks Call Center to check eligibility in NCFAST.
9 | Radiology | Claims | Missing or incorrect information on MedSolutions Prior Approvals is causing imaging claims to deny | Ongoing | MedSolutions, CSC and the State continue working to resolve oustanding issues. As of March 2, 2015, NCTracks can process claims for Lesser Intensity Procedures with Radiology PA from MSI. (https://www.nctracks.nc.gov/content/public/providers/provider-communications/2015-announcements/Paying-Claims-for-Lesser-Intensity-Procedures.html)
10 | Professional | Claims | Reprocessing of Claims for ACA Payments | Closed | The reprocessing of claims submitted from July 1, 2013 thru March 1, 2014 was completed in the March 11 checkwrite. The reprocessing of claims submitted before July 1 and Health Check was completed in the June 24 checkwrite. |  | 2014-06-24
11 | All | Enrollment | The current Office Administrator and Manage Change Request processes are impacting some providers | Closed | Changes to the Office Administrator process were implemented on January 4, 2015. Changes to the Manage Change Request process were implemented on August 2 2015. |  | 2015-08-02
12 | All | Eligibility | The Eligibility Response is lacking information that would be beneficial to providers | Closed | Improvements to the Eligibility Response were implemented on November 2 2014. |  | 2014-11-02
13 | All | Financial | Overpayments are not automatically recouped until 30 days, at which point interest penalties are assessed | Closed | This situation has been resolved. Accounts Receivables are now recouped beginning with the checkwrite following when they are established. |  | 2016-05-01
14 | All | Claims | Claims billed with 2014 CPT codes pended for "rate not on file" (or denied for "procedure code not on file") | Closed | The rates and edit updates for the 2014 CPT codes were completed on 3/9/14. Pended claims will automatically recycle. Denied claims will need to be resubmitted. |  | 2014-03-09
15 | All | Claims | Reprocessing of Crossover Claims (for revised "lesser-of" logic) | Closed | Completed in February 19 checkwrite. |  | 2014-02-19
16 | Institutional | Claims | Edit 00435 requiring HCPCS codes to be billed with Revenue Codes on Outpatient Hospital Claims | Closed | Edit changed to pay and report. Reprocessed denied claims at the direction of the State.
17 | All | Claims | What is the timeline on the "Shared Savings Plan"? We haven't had any funds withheld. Are there plans to recoup back to January 1? | Closed | See the September 2014 Special Medicaid Bulletin "3% Rate Reduction Update" at http://www.ncdhhs.gov/dma/bulletin/index.htm. ACA attested providers are exempt thru 12/31/14. The rates were changed on 5/23 for PCS providers. Recovery of PCS overpayments is occuring from September 2014 to April 2015. A letter was sent to affected PCS providers. The 3% reduction was applied to physician claims beginning March 2 2015. Reprocessing claims was done over 9 checkwrites beginning April 28 through June 23. | CSR 1642. Pending State re-write before doing ROM | 2015-06-23
18 | Institutional | Reporting | What is the expected target date for PS&Rs? How does claim reprocessing affect cost reports? | Closed | The process and form to obtain a detailed PS&R report is now available on the provider portal.
19 | All | Claims | Consent forms not approved are causing claims to deny | Closed | See the portal announcement re Common Errors on Consent Forms at https://www.nctracks.nc.gov/content/public/providers/provider-communications/provider-announcements/Common-Errors-on-Consent-Forms.html. Note that consent forms remain in system indefinitely, so claims can be refiled. Consent forms should be submitted by the performing surgeon's office with their NPI and recipient's RID written on the top of the form. See also the March 2014 Medicaid Bulletin.
20 | All | Claims | Some Pregnancy Medical Home codes are denying, even when billed with AF modifier | Closed | This issue was resolved on February 23. Providers will need to rebill the claims. All Pregnancy Medical Home claims, regardless of dates of service, require the AF modifier. |  | 2014-02-23
21 | Professional | Claims | Pregnancy Medical Home claims (S0280 and S0281) rendered by Nurse Practitioners and Physician Assistants are pending for "no fee on file" | Closed | This issue has been resolved. Pending claims have been released for processing in the July 22 checkwrite. No action is required by providers. New claims will process without pending. |  | 2014-07-22
22 | All | Claims | NCTracks claims processing change from legacy | Closed | NCTracks will audit the first detail line against itself, then, if paid, 1st line becomes history. It will then audit detail line 2 against detail line 1 and detail line 2, etc. The primary procedure code should always precede the add on code on the claim.
23 | All | Claims | Codes not payable with or without modifier 51 | Closed | This issue was resolved on 4/4. Providers can now resubmit claims. |  | 2014-04-04
24 | Institutional | Claims | Hospice vs Inpatient claim denial | Closed | This issue was resolved on 3/31. Providers can now resubmit claims. |  | 2014-03-31
25 | All | Claims | Some claims are pending for "fee not on file" or denying because the taxonomy code is not on file for the procedure code billed | Ongoing | The State continues to review codes and request system changes when needed. In many cases, the claims have adjudicated correctly. Remember, the code must appear on the appropriate fee schedule for it to be billable, but the presence of it on the fee schedule does not guarantee payment.
26 | All | Portal | Portal error messages including "IP Gateway" and "Input string" errors encountered when submitting a claim or prior approval request, as well as missing claim drafts or "favorites" used in provider portal claim submission | Closed | This issue was resolved March 28 |  | 2014-03-28
27 | Dental | Claims | Duplicate payments occurring on some dental codes, such as D1351 | Closed | This issue was resolved on April 19. The State is evaluating recoupment options. |  | 2014-04-19
28 | All | Prior Approval | "DMA" does not appear in the drop down list of Payers on the Provider Portal PA screens | Closed | This issue was resolved on April 12 |  | 2014-04-12
29 | All | Claims | Unable to save draft claims | Closed | This issue was resolved on April 12 |  | 2014-04-12
30 | All | Claims | Claims show as paid or denied when checking status on the portal, but do not appear on RA or EFT | Closed | This issue was resolved with the June 10 checkwrite |  | 2014-06-10
31 | Radiology | Claims | Billing lesser intensity for procedure codes in the same contrast family | Closed | See the provider portal announcement at https://www.nctracks.nc.gov/content/public/providers/provider-communications/provider-announcements/Outpt-Radiology-Claims-with-MSI-PA.html
32 | Anesthesia | Claims | Billing 0 units when CRNA present and using modifier AD as per policy | Closed | This issue has been resolved and the system is now able to process 0 units with AD modifier as policy instructs. Providers will need to resubmit denied claims.
33 | All | Enrollment | Issue with using the Manage Change Request application to add, change or remove the DBA name on the NCTracks provider record | Closed | This issue was resolved on January 4. |  | 2015-01-04
34 | DME | Claims | DME Claims are deducting co-pays in error | Closed | This issue was resolved on May 27. Awaiting direction from the State on a reprocessing plan |  | 2014-05-27
35 | Health Department | Claims | Some Health Department Claims (STD and TB services) are deducting co-pays in error | Closed | This issue has been resolved. Providers will need to resubmit denied claims. |  | 2024-02-11
36 | Various | Claims | Some Nutrition codes are denying with a BSG error | Closed | This issue was resolved on 6/22/14. Providers will need to resubmit denied claims. |  | 2014-06-22
37 | Auditory | Claims | Cochlear implants are denying for taxonomy error | Closed | This issue was resolved on July 21. Providers will need to resubmit denied claims. |  | 2014-07-21
38 | Anesthesia | Claims | Some anesthesia codes were denying for PA | Closed | This issue has been resolved. Providers will need to resubmit denied claims.
39 | Institutional | Claims | Proration issue when other insurance was involved | Closed | This issue was resolved on May 27. Awaiting direction from the State on a reprocessing plan |  | 2014-05-27
40 | All | Claims | Claims denying for no consent when a consent may not have been needed for the procedure performed | Closed | This issue has been resolved. Claims are now appropriately pending for nurse review. Providers will need to resubmit denied claims.
41 | Orthotic/Prosthetic Devices | PA | Some codes which do not require prior approval according to the fee schedule are denying for prior approval | Closed | This issue has been resolved. Providers will need to resubmit denied claims.
42 | All | Claims | If a claim has pended for incorrect Rendering Provider location, the portal screen is not populating the NPI or unmatched location, so it is not clear what needs to be corrected. | Closed | This issue was resolved on June 16. Updates were made to the existing messages in provider Inboxes, so providers can correct the incorrect location on the pended claims. |  | 2014-06-16
43 | All | Claims | Lab codes denied with EDIT 00527 ”LABORATORY SERVICES INCLUDED IN HOSPITAL REIMBURSEMENT” when the rendering provider is a Physician Assistant | Closed | This issue has been resolved. Providers will need to resubmit denied claims.
44 | All | Claims | Denials related to skin substitute diagnoses | Closed | Appligraf (procedure code Q4101) for diagnosis code series 707 was added January 13, 2015. Providers should resubmit denied claims. |  | 2015-01-13
45 | All | Claims | Claims denying due to codes not payable with modifier 59 with certain taxonomies | Closed | This issue was resolved on May 3, 2015. If a provider submitted a claim using 59 or one of the new modifiers prior to May 3 and received a denial, they can resubmit the claim. |  | 2015-05-03
46 | Dental | Claims | Some dental claims are being overpaid -is the fee schedule for some codes incorrect? | Closed | This issue was resolved on April 4, 2014 |  | 2014-04-04
47 | Speech Therapy | Claims | Speech Therapy claims are denying for "no fee on file" for the pricing provider (EOB 1660) and "procedure code invalid for rendering provider taxonomy" (235Z00000X) | Closed | This issue was resolved on 7/1/14. Providers will need to resubmit denied claims. |  | 2014-07-01
48 | Speech Therapy | Claims | Providers with taxonomy 235Z00000X cannot bill procedure code 92523 with modifier 52 | Closed | This issue is closed as of 9/22/14. Providers can resubmit denied claims and submit replacement claims for claims paid at incorrect amounts. |  | 2014-09-22
49 | DME | Claims | Procedure codes which have a national code, but the PA is issued for a state code, resulting in mis-match of the claim to the PA | Closed | This issue was resolved on July 21. |  | 2014-07-21
50 | Radiology | Claims | There are certain insurance types that should be bypassed for MedSolutions PA edit | Closed | This issue was resolved on July 14. |  | 2014-07-14
51 | Institutional | Claims | NCTracks is unable to process time limit overrides for secondary claims on a UB04 form. (See the July 11 newsletter article) | Closed | This issue was resolved on August 19, 2014. Providers should resubmit denied claims following UB-04 instructions. |  | 2014-08-19
52 | Institutional | Claims | Edit 02045 assigns EOB 00041 in error. If you have received this EOB, please resubmit a new claim with medical records | Closed | This issue has been resolved as of 10/6/14. Edit 2045 has correctly been assigned EOB 2105 - MEDICAL RECORDS IN SUPPORT OF PROCEDURE ARE REQUIRED. HOWEVER, A VALID CONSENT FORM IS ON FILE. |  | 2014-10-06
53 | Institutional | Claims | Edits 02040, 02041, and 02043 are assigning EOB 00041 in error. Refer to additional EOBs referenced on your Remittance Advice to clarify what is needed to resolve the claim issue | Closed | Edit 02040 is now properly assigned to EOB 00145, edit 02041 is now properly assigned to EOB 02101, and edit 02043 is now properly assigned to EOB 02013.
54 | Nursing Home | Claims | Claims were recouped in error as a result of DRG reprocessing | Closed | This issue was resolved on 8/11/14. Providers should resubmit claims for processing |  | 2014-08-11
55 | All | Claims | Cutback being applied to line items due to Carolina Access referral visit limit in error | Closed | New claims received as of 9/29/14 are not having a cutback issue. The issue was resolved on 11/9/14. Providers who had claims cutback in error can submit replacement claims. |  | 2014-11-09
56 | Optical | Claims | Claims denying for no PA for contact lens and some visual aids codes | Closed | This issue has been resolved. Providers will need to resubmit denied claims.
57 | Primary Care Providers | Secondary Claims | Reprocessing of legacy secondary claims for ACA payments resulted in zero dollar payment | Closed | This issue was resolved on 12/9/14. Providers can submit replacement claims. |  | 2014-12-09
58 | All | Claims | Claims denying stating both a sterilization and a hysterectomy consent form needed | Closed | This issue was resolved on 7/8/14. Claims will no longer deny for both procedures. Providers will need to resubmit denied claims. |  | 2014-07-08
59 | All | Claims | Claims denying for Edit 02020 without appropriate review | Closed | Claims are now pending for review. Providers will need to resubmit denied claims
60 | DME | Claims | The state codes, which must now be keyed with national codes K0108, A9900, B9998 and E1399 on the claim form, must have the alpha character capitalized (upper case). For example, e1399 is invalid, but E1399 is valid. | Closed | This issue was resolved on March 23, 2015 |  | 2015-03-23
61 | DME | Claims | Claims paying in error when provider bills a claim with modifier which differs from the service type on the prior approval | Closed | This issue is closed as of 9/26/14. Providers can submit replacement claims. |  | 2014-09-26
62 | All | Claims | Some claims are pending with Edit 1996 in error | Closed | This issue is resolved and the claims have adjudicated. No action required by providers.
63 | All | Medicare Part B Claims | Detail lines denied by Medicare are paying as Medicaid primary | Closed | Crossover claims now deny if Medicare denies. See Oct 30 announcement https://www.nctracks.nc.gov/content/public/providers/provider-communications/2015-announcements/Xover-Claims-To-Deny-If-Mcare-Denies.html |  | 2015-11-01
64 | Radiology | Claims | Claims are denying in error for lack of eviCore/MedSolutions PA when retroactive changes have been made to a recipient's TPL (other primary insurance) record. | Closed | This issue has been resolved. Providers can resubmit denied claims. |  | 2016-02-01
65 | DME | Claims | Claims with taxonomy code 332BX2000X are denying with a BSG error | Closed | This issue was resolved on August 31, 2014. Providers should resubmit denied claims. |  | 2014-08-31
66 | All | Enrollment | Periodic internal errors when accessing credentialing Change Requests, Applications and Reverifications | Closed | This issue is closed. If an error message is received, providers should contact NCTracks so that cause can be identified. |  | 2019-04-08
67 | DME Diabetic Supply Codes | Prior Approval and Claims | Prior Approval for codes A4253, A4256, A4258, and A4259 do NOT require modifier U9. SC modifier is no longer required and EOB 01841 is in need of revision. | Closed | This issue was resolved on 11/26/14. Implemented new wording to EOB 01841. |  | 2014-11-26
68 | All | Enrollment | Some providers are receiving a denial dispute approval letter when the file is sent over to DMA for review | Closed | This issue was resolved on 8/18/14. Verified that currently it is working as designed. |  | 2014-08-18
69 | All | Enrollment | Some providers are receiving both approval and denial letters for the same application | Closed | This issue was resolved on 9/22/14. |  | 2014-09-22
70 | All | Enrollment | Some providers are finding that when there is a change in Office Administrator, the NCID of the new OA displays the name of the former OA | Closed | This issue has been resolved.
71 | All | Claims | Chemotherapy administration codes are denying against primary procedure codes | Closed | This issue was resolved on 12/5/14. |  | 2014-12-05
72 | Professional | Claims | T2041 shows an incorrect effective date for CAPCO Benefit Plan | Closed | This issue is closed.
73 | Professional and Facilities | Claims | Assistant Surgeons and Co-Surgeons are receiving denials for Prior Approval in error. (Some primary physicians were also affected by facilities utilizing the units from the PA.) | Closed | This issue was resolved on March 2. The units have now been restored to the PAs. Professional providers can resubmit their claims. |  | 2015-03-02
74 | Professional | Claims | Various procedure codes billed under the CAP programs denying for TPL suspect | Closed | This issue was resolved on 11/30/14. Providers can resubmit denied claims. |  | 2014-11-30
75 | Health Choice | Claims | Due to an issue in the changeover to the new federal fiscal year, Health Choice claims were not processed in the October 7 checkwrite. | Closed | The issue has been corrected and these claims were re-cycled and processed in the October 15 checkwrite. No action is required on the part of Health Choice providers. |  | 2014-10-15
76 | Nursing Home | Claims | Retroactive nursing home rate adjustments for Q2 were applied 9/23/14. When the claims were reprocessed for payment at the new rate, the PML was withheld on each claim during the month. | Closed | The claims that had the rate change were voided and reprocessed in the October 15 checkwrite as original claims to correct the issue with PML. |  | 2014-10-15
77 | Public Health | Prior Approval | EHDI is not displayed in the Prior Approval drop down list on the portal | Closed | This issue was resolved on 11/2/14 |  | 2014-11-02
78 | Dental and Orthodontic | Claims | Claims are denying for non-covered codes with EOB 02310 and prior approval is on file. | Closed | This issue has been resolved. Dental non-covered services are being paid correctly. Providers can rebill denied claims.
79 | Pharmacy | Claims | Copaxone is currently rejecting at pharmacies for MAX QUANTITY EXCEEDED. Currently, only TWO SYRINGES may be submitted at a time. The patient may have to return to the pharmacy in two days to receive additional medication. | Closed | This issue was resolved on 11/7/14. |  | 2014-11-07
80 | All | Claims | The influenza virus vaccine is denying due to age and therefore causing the administration code to deny as well. (Codes 90687 and 90688) | Closed | This issue was resolved on November 9, 2014. Affected providers should resubmit denied claims. |  | 2014-11-09
81 | Institutional | Claims | Claims are denying or cut back with Edit 254 and/or Edit 262 and/or Edit 279 when recipient is partially eligible during their inpatient stay | Closed | This issue has been resolved. |  | 2016-12-09
82 | All | Claims | Medicare Part C claims are denying with Edit 269 when recipient has MQB program coverage | Closed | This issue was resolved on March2 2015.
83 | All | Claims | Claims are pending for edit 00142 (UNITS NOT EQUAL TO DOS) in error | Closed | This issue was resolved on November 24, 2014. Claims which should not have been pending for edit 00142 have been released. If your claim is still pending for edit 00142 it is pending for a valid reason and will be released after review. No provider action necessary. |  | 2014-11-24
84 | Health Department | Claims | The influenza virus vaccine is denying for Health Departments due to invalid taxonomy. (Codes 90687 and 90688) | Closed | This issue was resolved on November 20, 2014. Providers can resubmit previously denied claims. |  | 2014-11-20
85 | All | Claims | 89240 shows an incorrect effective date causing claims to pend in error | Closed | This issue was resolved on 12/4/14. No action required by providers. |  | 2014-12-04
86 | Optical | Prior Approval | Approval letters are not going out for Visual Aids that have been Auto Approved since about week of November 17, 2014. | Closed | This issue was resolved on 12/29/14. |  | 2014-12-29
87 | Optical | Claims | Dispensing Claims for PA's approved under the incorrect health plan had not been paying since mid October. | Closed | Claims now paying. If providers have a denied claim, they can resubmit. ( and providers are reminded to use actual dispense date as Date Of Service for dispensing glasses).
88 | All | Claims | Hysterectomy claims which have records attached may deny for edit 02045/EOB 02105 when the DX is PID, mild/moderate cervical dysplagia, CA in situ of unsp organs, uterine hemorrhage from placenta previa. | Closed | This issue was resolved on March 13, 2015. Providers can rebill denied claims. |  | 2015-03-13
89 | All | Claims | Essure sterilization follow-up services 58340 and 74740 are denied for edit 00198/EOB 00041 (Federal sterilizaiton consent form guidelines not met) when correctly billed. | Closed | This issue was resolved on April 28. Providers can resubmit denied claims. |  | 2015-04-28
90 | All | Claims | Hysterectomy claims for recipients who were sterile prior to the hysterectomy are denied for edit 00199/EOB 02013 (hysterectomy consent for guidelines not met) when consent information has been correctly submitted and approved. | Closed | This issue has been resolved as of 1/12/2015. Providers should be able to resubmit claims previously denied due to this issue. |  | 2015-01-12
91 | All | Claims | Hysterectomy claims denied for edit 00198/EOB 00041 (Federal sterilizaiton consent form guidelines not met) when there is a valid hysterectomy consent on file. | Closed | Providers will need to submit a paper claim with the Medicaid adjustment request form and records. |  | 2015-11-20
92 | All | Eligibility | Recipient inquiries were not showing their PCP info because the provider had end dated the location the Carolina Access people were tied to | Closed | This issue has been resolved.
93 | FQHC/RHC | Claims | As of 12/21, FQHC / RHC claims are denying for edit 00434 (Rendering taxonomy invalid for procedure ) when billing procedure code T1015 | Closed | This issue was resolved on January 18. Providers with claims that denied for Edit 00434 may resubmit the claims for processing. |  | 2015-01-18
94 | DME and PCS | Claims | Beginning December 21, DME and PCS claims have been denying for Edit 00434 (Rendering taxonomy invalid for procedure ). | Closed | This issue was resolved on January 18. Providers with claims that denied for Edit 00434 may resubmit the claims for processing. |  | 2015-01-18
95 | All | Claims | Some providers have reported that NC Tracks is running slowly when keying and submitting claims into the secure Provider Portal, particularly when entering information in the Other Payer tab, but also with Primary Payer input | Closed | This issue appears to have been an intermittent problem and is no longer being reported.
96 | All | Prior Approval | Some providers have reported that they are not receiving prior approval (PA) letters in their Message Center Inbox. | Closed | This issue is closed.
97 | All | Claims | Claims which include Sterilization billed with ICD 9 code 6919 denied for edit 02040/EOB 00145 (no hysterectomy statement on file) when there is no hysterectomy performed. | Closed | Providers will need to submit a paper claim with the Medicaid adjustment request form and records. |  | 2015-11-20
98 | All | Claims | For providers using the browser Internet Explorer version 8, when they key claim information into the Other Payers tab on the portal and then click "Save", the payer information they entered is cleared out without saving. | Closed | This issue has been resolved
99 | All | Prior Approval | Subsequent prior approval requests are being automatically voided by the system as a duplicate if there is a previous denial for the same services. | Closed | This issue was resolved on 11/3/15. |  | 2015-11-03
100 | All | Claims | When a provider enters that primary insurance has paid 0 dollars on the claim and they indicate why it did not pay, the system is not reading it and is denying the claim saying TPL needs to be billed. | Closed | This issue was resolved on February 6, 2015. Providers can rebill denied claims. |  | 2015-02-06
101 | Institutional | Claims | Some claims have processed and paid with DRG Grouper version 30 instead of DRG version 31. | Closed | This issue was resolved on February 22, 2015 |  | 2015-02-22
102 | All | Claims | Some claims with certain unlisted procedure codes are pending because they cannot currently be priced | Closed | This issue was resolved on February 22, 2015. Claims should continue processing. |  | 2015-02-22
103 | All | Claims | In addition to FQHC/RHC, DME and PCS claims, providers have reported that hearing aid, chiropractic, ambulatory surgery, and behavioral health services claims have been denying for Edit 00434 (Rendering taxonomy invalid for procedure ). | Closed | This issue was resolved on January 18. Providers with claims that denied for Edit 00434 may resubmit the claims for processing. |  | 2015-01-18
104 | Nursing Home | Claims | SNF Rates have not been updated | Closed | Rates have been updated in NCTracks and notification posted. |  | 2015-02-13
105 | All | Claims | The Signature Date for hysterectomy consents are being displayed incorrectly as Procedure dates on the Provider Consent page. | Closed | This issue is closed.
106 | DPH | Claims | DPH providers have reported an issue that is causing DPH claims to deny with Edit 05415 / EOB 05415 - TPL NOT SUBMITTED ON CLAIM. PLEASE RESUBMIT WITH TPL CLAIM LINE DETAILS. | Closed | This issue was resolved on March 8, 2015. Providers can rebill denied claims. |  | 2015-03-08
107 | Dental | Provider | When checking Dental Benefit Limitations on the Provider Portal to determine if a beneficiary is eligible for certain time limited services (x-ray history , appliance and sealant history) the information that displays appears to be incorrect. | Closed | This was determined to be working as designed. Providers are encouraged to print out the information when the limitations are checked. If the provider provides treatment based on incorrect information and the claim denies, the provider should submit a prior approval request with the screen shots of the dental benefit limitations page showing incorrectly and a brief statement of why the services are being submitted for prior approval. |  | 2016-01-07
108 | Dental | Prior Approval | Providers periodically report having trouble being able to upload documents to an existing prior approval using the provider portal | Closed | This issue is sporadic. Providers are encouraged to try FireFox browser to accomplish this task. If unable to upload documents to an existing PA, the provider should contact the Call Center and request submission of a ticket to have the issue investigated. |  | 2018-02-15
109 | Dental | Claims | Problems with billing of D0145 and D1206 | Closed | Claims including these codes should be billed as follows in order for both procedure codes to be paid correctly: D1206 must be billed on the detail line before D0145. NCTracks adjudicates one detail line at a time. NCTracks must recognize that D1206 has been paid before the exam D0145 can be paid for the date of service. This is working as designed. |  | 2015-04-01
110 | Pharmacy | Claims | There is an issue where if the third party (NOT Medicare part D) pays at least 60% of the allowable, it should bypass any pa criteria. Currently claims deny saying it needs a PA. | Closed | This issue has been resolved. Providers will need to resubmit denied claims. |  | 2015-07-15
111 | All | Claims | There is an issue with Part C claims for Q class recipients in which the cost share was inappropriately cut back or denied. Several types of claims may have been affected, including durable medical equipment, endoscopy claims, or some dental procedures. | Closed | This issue was resolved on April 19. If providers have a Medicare primary claim for a Q class recipient that had cost share cut back or denied, they can resubmit denied charges or replace claims that paid incorrectly. |  | 2015-04-19
112 | Institutional | Claims | The occurrence code used to indicate that Medicare Part A was exhausted on institutional claims, but it does not work that way in NCTracks. | Closed | This issue has been resolved. See Announcement posted March 29, 2018. https://www.nctracks.nc.gov/content/public/providers/claims/secondary-claims/secondary-claims-announcements/New-Pricing-Methodology-for-Exhausted-Medicare-Part-A-Benefits-on-Crossover-Claims.html |  | 2018-03-29
113 | Professional | Claims | For dates of service on reprocessed claims from January 1 to June 30, 2013, if the rendering provider taxonomy code is PA, there is no Medicare percentage rate, so it pays at zero percent. | Closed | This issue has been resolved.
114 | Health Check | Claims | Claims are denying with TJ modifier. The Edit posted is 2104 - Provider Taxonomy Not Allowed for Modifier Submitted. | Closed | This issue was resolved on May 8, 2015. Claims that were pended will recycle and process automatically |  | 2015-05-08
115 | Dental | Claims | Dental Fee Schedule on the DMA website does not show codes exempted from 3 pct reduction | Closed | This issue is resolved
116 | Institutional | Claims | Institutional claims are denying for edit Edit 00344 FAMILY PLANNING INDICATOR NOT IDENTIFIED when ICD9 procedure 66.52 is reported on claim. | Closed | Providers need to submit the Medicaid Adjustment Request form, claim, and medical records. |  | 2016-02-24
117 | NCHC | Claims | NCHC claims for CPT code 78802 and 78803 with DOS 7/1/13 and forward are denying for Prior approval required. | Closed | This issue was resolved on June 24, 2015. Providers can resubmit claims that denied for this issue. |  | 2015-06-24
118 | DME | Claims | K0739 is a general labor code used for any repairs/ replacement for typically any DME code. It is restricted to 4 specified Out of State providers for speech generating devices. However, when providers bill for other repairs, the claims are denying. | Closed | This issue was resolved on 10/30/15. Providers can resubmit claims that denied for this issue. |  | 2015-10-30
119 | Behavioral Health | Provider | Some mental and behavioral health providers were automatically enrolled in NCTracks through their local LME/MCO. Some of these records were received with incorrect data, which is preventing providers from updating their registration. | Closed | Affected providers should submit a letter to CSC via mail or fax on company letterhead signed by an authorized individual attesting to the correct NPI, Name, DOB, SSN/EIN.
120 | All | Claims and Prior Approval | Issue with entering diagnosis codes on claims and PAs keyed into the portal. Previously, a diagnosis code could be entered with or without the decimal point, but currently an invalid diagnosis code error will post if decimals or spaces are used. | Closed | This issue was resolved on July 8, 2015 |  | 2015-07-08
121 | All | Enrollment | When a provider enters a DEA effective date, the system is defaulting to the current date and it can't be changed. | Closed | This issue has been resolved. |  | 2016-11-20
122 | All | Enrollment | Some providers have an end-date on their Currently Enrolled Provider (CEP) Authorization Code, which will cause an error when completing the Office Administrator (OA) Change Process | Closed | This issue has been resolved. If it should re-occure, providers can call the Contact Center and ask them to send a ticket to Enrollment to remove the end date. |  | 2016-05-24
123 | Chiropractors | Claims | Some chiropractic services have recently denied with EOB 01171 - DIAGNOSIS REQUIRES SUPPORTING DOCUMENTATION. RESUBMIT AS A ADJUSTMENT WITH MEDICAL RECORDS. | Closed | Claims submitted based on DMA policy should now be processing correctly. Providers may resubmit claims which previously denied, through their regular claim submission method and not as a paper adjustment. |  | 2015-09-21
124 | All | Claims | Manually priced items (such as J3490) and Adjustments paid $0 when reprocessed to recoup 3% rate reduction | Closed | This issue was resolved by 12/31/15. |  | 2015-12-31
125 | Family Planning | Claims | Inter-periodic exams (99201-99205, 99211-99215, RC 510 and 519) are denying for missing annual exam date. | Closed | This issue was resolved on 10/9/15 |  | 2015-10-09
126 | Family Planning | Claims | Claims are denying for edit 00344. | Closed | This issue was resolved on 10/9/15 |  | 2015-10-09
127 | All | Enrollment | Providers periodically receiving error when submitting application, MCR, etc. indicating "Unable to Retrieve/Submit Manage Change Request Application." This issue is intermittent. | Closed | This issue was resolved on 12/31/15 and MCRs can now be resubmitted. |  | 2015-12-31
128 | All | Claims | Some providers were overpaid in the September 15 checkwrite and then had AR's created with the September 22 checkwrite. | Closed | This issue is resolved.
129 | All | Claims | Claims billed with modifier 26 are denying for edits 00152 and 00431. | Closed | This issue was closed on 12/10/15. |  | 2015-12-10
130 | All | Claims | Claims were denying for Edit 00097 indicating the receipient was incarcerated on the DOS. | Closed | This issue was related to the synchronization of the eligibility file with NCFAST and is now resolved. |  | 2015-10-05
131 | All | Claims | Some adult preventative medicine annual health assessments billed with diagnosis Z00.00 have been denying for Edit 00063 - REFGE RECIP MUST PRIM DX V705. | Closed | This issue is expected to be resolved on 11/1/15, after which affected providers can resubmit denied claims. |  | 2015-11-01
132 | All | Prior Approval | Prior approval requests are denying when lowercase letter is used in diagnosis code submitted. | Closed | This issue is resolved. |  | 2015-11-11
133 | All | Claims | Some providers have recently had J-code claims deny for Edit 02672 - J CODE AND GCN COMB IS INVALID and Edit 02673 - NDC/GCN + ICD COMBO IS INVALID. In some cases, this may have happened with a drug that does not require a diagnosis code for billing. | Closed | This issue has been resolved. It is now working as designed. Providers can resubmit previously denied claims. |  | 2016-01-22
134 | All | Claims | Claims with diagnosis N39.3 have denied for Edit 00194 - DIAG INVLD FOR RECIP SEX | Closed | This issue was resolved on 10/12/2015. Providers can resubmit claims that denied for this issue. |  | 2015-10-12
135 | All | Claims | An issue caused claims for Medicaid Pregnant Women (MPW) patients to deny incorrectly for presumptive eligibility | Closed | This issue is resolved. Providers should no longer send claims to the DMA call center for research and approval. Providers can now rebill the MPW claims that denied for presumptive eligibility. |  | 2015-10-20
136 | All | Claims | Claims for preventive visits using Z00.111 and Z00.110 are denied for edit 04506 - procedure is invalid for the diagnosis / EOB 00082 SERVICE IS NOT CONSISTENT WITH/OR NOT COVERED FOR THIS DIAGNOSIS/OR DESCRIPTION DOES NOT MATCH DIAGNOSIS. | Closed | This issue was resolved on 10/30/2015. Providers can resubmit claims that denied for this issue. |  | 2015-10-30
137 | All | Claims | Some claims for J9035 which were billed with required diagnoses are denying for edit 04506 - procedure is invalid for the diagnosis / EOB 00082 SERVICE IS NOT CONSISTENT WITH/OR NOT COVERED FOR THIS DIAGNOSIS/OR DESCRIPTION DOES NOT MATCH DIAGNOSIS. | Closed | This issue was resolved on 1/12/2016. Providers can resubmit claims that denied for this issue. |  | 2016-01-12
138 | All | Claims | Claims billed with diagnosis Z23 have denied for edit 00153 - procedure is invalid for the diagnosis / EOB EOB 00082 SERVICE IS NOT CONSISTENT WITH/OR NOT COVERED FOR THIS DIAGNOSIS/OR DESCRIPTION DOES NOT MATCH DIAGNOSIS | Closed | This issue was resolved on 10/21/2015. Providers can resubmit claims that denied for this issue. |  | 2015-10-21
139 | All | Enrollment | End-dating an owner or managing employee is requiring provider to enter physical residential address, email address, and phone number | Closed | This issue is resolved as of 12/16/15. Please delete any saved drafts with this error. |  | 2015-12-16
140 | Hospice | Claims | Some hospice claims for dates 10/1/2015 and after are being denied for edit 00218 | Closed | This issue is now resolved. Pending claims will be released this week and should continue processing. |  | 2015-12-21
141 | All | Claims | Claims for procedure code 90651 billed with diagnosis codes Z00.121 or Z00.129 are denying with EOB 00082 - SERVICE IS NOT CONSISTENT WITH/OR NOT COVERED FOR THIS DIAGNOSIS/OR DESCRIPTION DOES NOT MATCH DIAGNOSIS | Closed | This issue was closed 11/17/15 |  | 2015-11-17
142 | Health Choice | Claims | There are claims denying with edit 00152 when the TJ modifier is billed for NCHC recipients under the age of 6 covered under MIC-J program. Affected codes include 99381, 99382, 99391 and 99392. | Closed | This issue has been resolved. Provider can now resubmit denied claims. |  | 2016-02-02
143 | All | Enrollment | Some providers have found that currently listed individuals in the Managing Relationship section in NC Tracks are populating in the Managing Relationship section in a new Manage Change Request with the SSNs missing. | Closed | This issue was closed 12/16/15. |  | 2015-12-16
144 | All | Enrollment | When an individual provider record is updated for an NPI that has not previously been accessed in NCTracks (CEP registration has not been completed), the name of organizations who share the same EIN is changed to the last name of the individual provider. | Closed | This issue has been resolved. |  | 2016-03-23
145 | Family Planning | Claims | Claims are denying for edit 00344 with ICD-9 diagnosis codes. | Closed | This issue was resolved on 12/11/15. Claims billed with FP ICD-9 diagnosis codes after 10/1/15 that denied for edit 00344 can be resubmitted. |  | 2015-12-11
146 | Radiology | Claims | Claims for Ultrasounds are denying for edit 55930 for medical necessity with MedSolutions (eviCore) PA on file | Closed | This issue was resolved on 12/15/15. Providers can now resubmit denied claims. |  | 2015-12-15
147 | DME | Claims | DME claims are currently denying for edit 00222 Required Prior Approval Missing when a lifetime PA has been granted | Closed | Issue #166 is a superset of this issue and provides additional information |  | 2016-01-21
148 | All | Eligibility | When providers check the portal or AVRS, the information they may receive conflicts with NCFAST regarding the PCP of the recipient. | Closed | No longer an issue. |  | 2017-03-13
149 | All | Claims | 54 Modifier "surgical care only," used for reimbursement for major or minor surgery, is causing this service to pay $0. | Closed | Duplicate of issue #152 |  | 2016-01-20
150 | All | Claims | Procedure code 78804 with modifier 26 is denying for edit EOB 00156 LABORATORY REVENUE CODE REQUIRES CORRESPONDING LAB CPT CODE ENTER CPT CODE AND SUBMIT AS A NEW CLAIM. | Closed | This issue was resolved on 3/17/16. Providers will need to resubmit denied claims. |  | 2016-03-17
151 | All | Claims | Procedure code 22614 is denied for edit 32080 when billed with 22630 and 22633 | Closed | This issue was resolved on 3/31/16. Providers will need to resubmit denied claims. |  | 2016-03-31
152 | All | Claims | Modifier 54 is paying $0 when billed with procedure 66761. | Closed | This issue has been resolved. Affected providers should submit a corrected claim. |  | 2016-11-23
153 | All | Claims | When procedure codes 33264, 33221, 33223, 33228, 33229, 33230, 33231 are billed as an add-on to procedure code 33263, claims are denying edit 35800 INSERTION OF PACING ELECTRODE MUST BE BILLED WITH PRIMARY PROCEDURE. | Closed | This issue was resolved on 2/28/16. Providers will need to resubmit denied claims. |  | 2016-02-28
154 | All | Claims | Claims are denying with add on procedure code 33924 for Edit 32200 - ADD ON CODE MUST BE BILLED WITH PRIMARY. | Closed | This issue was resolved on 10/19/16. Affected providers can rebill denied claims. |  | 2016-10-19
155 | Institutional | Claims | Critical Access hospitals are receiving denials when billing for revenue code 0615 in conjunction with procedure 70544. The edit that is posting is edit 00146 PROCEDURE CODE INVALID FOR BILLING PROVIDER TAXONOMY. | Closed | This issue is resolved. Affected providers can resubmit denied claims. |  | 2016-08-23
156 | All | Claims | Claims are denying with add on procedure code 93571 for Edit 34000-ADD-ON CODE M/B BILL PRIMARY | Closed | This issue was resolved on 3/12/16. Providers will need to resubmit denied claims. |  | 2016-03-12
157 | All | Claims | Claims are denying with add on procedure codes 58110 or 58611 for Edit 21940-ADD ON CODE MUST BILL W/ PRIME | Closed | This issue was resolved on 3/16/16. Providers will need to resubmit denied claims. |  | 2016-03-16
158 | Pathology | Claims | Pathology codes 87624, 87623, 87625 are receiving denials for edit 00358-FACTOR CD IND PROC NON-CVRD /EOB 05203 SERVICE REPRESENTED BY THIS PROCEDURE CODE/MODIFIER COMBINATION IS NOT COVERED BY THE NC MEDICAID PROGRAM. | Closed | This issue is resolved. Affected providers can rebill denied claims. |  | 2016-01-13
159 | Chiropractors | Claims | some claims for dates of services 10/1/2015 and after have been denied for EOB 01171 - DIAGNOSIS REQUIRES SUPPORTING DOCUMENTATION. RESUBMIT AS A ADJUSTMENT WITH MEDICAL RECORDS. However, these denials cannot be resolved through the adjustment process. | Closed | This issue has been resolved. Providers can resubmit the denied claims. |  | 2016-07-14
160 | All | Financial | A software upgrade on December 12 resulted in the RA font reverting to its previous size, affecting RAs produced in checkwrites beginning December 15 | Closed | This issue has been resolved.
161 | All | Claims | Procedure Code 01965 is denying when billed with ICD 10 diagnosis codes. | Closed | This issue was resolved on 3/8/16. Providers will need to resubmit denied claims. |  | 2016-03-08
162 | Pharmacy | Claims | Drug code J0585 is denying for edit 4506 PROCEDURE IS INVALID FOR THE DIAGNOSIS when billed with ICD10 diagnosis G82.20. | Closed | This issue is currently being researched. An update will be posted when more information is available. |  | 2016-01-27
163 | All | Claims | Procedure code 99385 is denying for some ICD 10 diagnosis codes Edit 04506 and 00153 PROCEDURE IS INVALID FOR THE DIAGNOSIS. | Closed | This issue has been resolved. Affected providers can resubmit denied claims. |  | 2016-05-10
164 | All | Claims | For dates of service prior to 10/1/15 procedure code 95079 is denying for Medically Unlikely Edit when more than 2 units are billed. | Closed | This issue has not re-occurred. |  | 2016-08-17
165 | All | Enrollment | When a provider fills out the Re-verification application they receive the message "Please complete a Manage Change Request to update your record," but when the MCR is approved the address for the individual provider isn't saved. | Closed | This issue was resolved on February 7, 2016. |  | 2016-02-07
166 | All | Claims | Some services which require PA are denying for edit 00222 / EOB 00023 because of changes to the recipient's ID after the original PA was granted. Primarily with DME and orthodontic PA, but not restricted to those services. | Closed | This issue was resolved on 2/15/16. Affected providers can now resubmit denied claims. |  | 2016-02-15
167 | All | Claims | J0585 when billed with diagnosis G82.20 is denying for edit 4506 - SERVICE IS NOT CONSISTENT WITH/OR NOT COVERED FOR THIS DIAGNOSIS/OR DESCRIPTION DOES NOT MATCH DIAGNOSIS. | Closed | This issue was resolved on 1/27/16. Affected providers can now resubmit denied claims. |  | 2016-01-27
168 | All | Claims | Procedure codes 41010 and 41115 when billed with secondary diagnosis P92.9 are being denied for edit 222 REQUIRED PA MISSING. | Closed | This issue was resolved on 2/25/16. Affected providers can now resubmit denied claims. |  | 2016-02-25
169 | All | Claims | Add on code 95874 when billed with primary code 64615 is denying for edit 37140 Elec. Stimulation Must be billed W/Primary | Closed | This issue has been resolved. Providers will need to resubmit the denied claims. |  | 2016-09-15
170 | Ambulance | Claims | Some ambulance claims are denying for edit 01212 / EOB 01806 when the AM condition code is used. | Closed | This issue was resolved on 2/13/16. Providers will need to resubmit the denied claims. |  | 2016-02-13
171 | Institutional | Claims | Revenue code 0637 Self administered drugs are currently pending for edit 00148 PROCEDURE CODE\REVENUE CODE INVALID FOR PLACE OF SERVICE | Closed | This issue was resolved on March 3, 2016. |  | 2016-03-03
172 | Family Planning | Claims | Some claims are denied for edit 00344 when billed with diagnosis Z049 or when recipient is enrolled as MAFDN - Medicaid Family Planning | Closed | This issue has been resolved. Affected providers can resubmit denied claims.
173 | All | Claims | Procedure code 22614 is denying for Edit 32080 ADD-ON CODE MUST BE BILLED WITH THE PRIMARY CODE. | Closed | This issue was resolved on 3/31/16. Providers will need to resubmit the denied claims. |  | 2016-03-31
174 | All | Claims | Mammography screening for ages 35-40; procedure codes G0202 and G0206, are denying for edit 4506 SERVICE IS NOT CONSISTENT WITH/OR NOT COVERED FOR THIS DIAGNOSIS/OR DESCRIPTION DOES NOT MATCH DIAGNOSIS when billed with diagnosis code Z12.31. | Closed | This issue was resolved on 4/8/16. Providers will need to resubmit the denied claims. |  | 2016-04-08
175 | Institutional | Claims | Revenue code 0637 Self administered drugs are currently pending for edit 00148 PROCEDURE CODE\REVENUE CODE INVALID FOR PLACE OF SERVICE. | Closed | This issue was resolved on 2/29/16. Providers will need to resubmit the denied claims. |  | 2016-02-29
176 | All | Claims | J9303 was denying for edit 04506 Procedure Is Invalid for the Diagnosis. | Closed | This issue has been resolved. Providers can resubmit denied claims. |  | 2016-03-23
177 | All | Claims | Procedure code 90460 when billed with more than 2 units is denying with edit 2241 IMMUNIZATION ADMINISTRATION NOT ALLOWED WITHOUT BILLING THE APPROPRIATE IMMUNIZATION CODE. | Closed | This issue has been resolved. Affected providers can resubmit denied claims. |  | 2016-06-08
178 | All | Claims | Procedure code 64640 is denying for audits 32700 MORE THAN 1 MOD 55 SURG W/O 51 and 33040 SURGICAL PROCEDURES LIMITED TO TWO PER DAY to allow 2 units only. | Closed | This issue has been resolved. Providers can resubmit the denied claims. |  | 2016-07-14
179 | All | Claims | Procedure code 70544 is denying when billed with the taxonomy 282NC0060X-Critical Access for edit 00146 PROCEDURE CODE INVALID FOR BILLING PROVIDER TAXONOMY. | Closed | This issue has been resolved. Affected providers can resubmit denied claims. |  | 2016-08-17
180 | DPH | Claims | DPH claims for specialized therapies (OT, PT, ST) were denying for PA | Closed | This issue has been resolved. Providers can resubmit the denied claims. |  | 2016-02-22
181 | All | Claims | Procedure code J1756 is denying for edit 04506 PROCEDURE IS INVALID FOR THE DIAGNOSIS/ EOB 00082 SERVICE IS NOT CONSISTENT WITH/OR NOT COVERED FOR THIS DIAGNOSIS/OR DESCRIPTION DOES NOT MATCH DIAGNOSIS when billed with DX D50.9. | Closed | This issue was resolved on 3/25/16. Providers can resubmit the denied claims. |  | 2016-03-25
182 | Podiatry | Claims | Some providers have reported Podiatry denials for SERVICES RENDERED BY PODIATRIST REQUIRES SPECIFIC DIAGNOSIS . | Closed | This issue has been resolved. Affected providers can resubmit denied claims. |  | 2016-05-02
183 | All | Claims | SNF and PCS claims are denying in error for edit 13400 SUSPECT DUPLICATE-OVERLAPPING DATES OF SERVICE when the hospital admission date differs from the From date of service. | Closed | This issue was resolved on 4/11/16. Providers can resubmit the denied claims. |  | 2016-04-11
184 | All | Enrollment | Some provider records were suspended during March, when they should not have been. All of the affected providers had previously submitted a Manage Change Request (MCR), which is currently in review status. | Closed | This issue has been resolved. The suspension on these provider records has been lifted and their deadlines for completion of the re-credentialing process extended accordingly. |  | 2016-03-23
185 | All | Prior Approval | There is an issue with the CASEHEAD IDs being sent from NCFast in some cases. When the NCFAST casehead ID and NCTracks casehead ID don't match, PA letters are not being generated. | Closed | This issue is resolved |  | 2018-02-15
186 | All | Enrollment | There is an issue with the Re-credentialing process in which submission of a Manage Change Request (MCR) or Re-credentialing application does not automatically lift the provider suspension. | Closed | This is currently working. Exceptions are being dealt with on a case-by-case basis. Once the MCR or re-credentialing application has been submitted, providers should wait 24 hours for suspension to be lifted. |  | 2016-08-17
187 | All | Claims | Some appendectomies are being denied for edit 00153 / EOB 00082. Diagnoses which deny are K35.2 and K35.3. | Closed | This issue was resolved on 4/22/16. Providers can resubmit the denied claims. |  | 2016-04-22
188 | DPH | Claims | Some ITP CCE services are pending for edit 4504 - FS50008 NO CAC/INVALID INPUT/SYSTEM ERROR | Closed | Pended claims should automatically recycle. Denied claims will need to be resubmitted. |  | 2016-05-25
189 | All | Enrollment | When submitting an application, if provider receives an error message indicating the email address associated with the provider record is not valid, the provider will not be able to pay for or cancel the application | Closed | This situation has been largely resolved. If this situation occurs, the provider should contact the NCTracks Call Center and request a ticket be logged for the Enrollment team |  | 2016-06-08
190 | Anesthesia | Claims | Anesthesia claims with add on codes are denying for EOB 01432 - DETAIL BILLED WITH INCORRECT OR NO MODIFIER. CORRECT DETAIL AND RESUBMIT AS A NEW DAY CLAIM. IF REIMBURSEMENT AFFECTED, REQUEST A FULL RECOUPEMENT AND RESUBMIT CLAIM | Closed | All affected providers can now resubmit any denied claims |  | 2017-11-16
191 | All | Claims | Some providers have reported claim denials for Edit 00805 RECIPIENT 21 OR OVER REQUIRES SPECIFIC DIAGNOSIS FOR BILLED PROCEDURE. | Closed | All impacted providers would need to resubmit the denied claims. |  | 2017-06-15
192 | All | Claims | Claims for 96110 with EP modifier are pending for no rate on file due to recent file updates. | Closed | This issue is resolved. Pended claims will recycle automatically. No action is required. |  | 2016-08-17
193 | All | Claims | Providers are receiving denials for pcode J2785 with Edit 39850 and EOB 02119 REGADENOSON MUST BILL WITH CARDIOVASCULAR IMAGING OR STRESS TEST PROCEDURES | Closed | This issue is resolved. Affected providers can rebill denied claims. |  | 2016-08-02
194 | All | Claims | Claims submitted for code 43248 and a code from the same family on same date are pricing the 1st code at the allowable amount and the 2nd code at 50% of allowable, rather than pricing the second code at allowable minus base code (43235) allowable. | Closed | This issue has been resolved |  | 2016-12-13
195 | DPH | Claims | ITP claims have denied procedure 97750 for edit 04506/EOB 00082 when billed with ICD-10 diagnosis code. | Closed | This issue is closed. The system is working correctly. |  | 2016-06-02
196 | All | Claims | Claims billed with procedure 49905 are denied for edit 32350 / EOB 7959 - NO PAYMENT FOR ADD-ON (ZZZ) CODE ALLOWED IF 'PRIMARY' CODE IN SERIES IS NOT PAID FOR THE SAME DATE OF SERVICE, SAME PROVIDER​. | Closed | This issue is resolved. Affected providers should refile the denied claims. |  | 2016-08-31
197 | All | Claims | On the provider portal, when provider submits an adjustment and selects DE 1284 Claims Attachment Type Code OZ and DE 1285 Claims Attachment Transmission Code EL, the row for the attachment DCN is not inserted. | Closed | This issue is resolved. Affected providers can resubmit claims. |  | 2016-08-15
198 | Outpatient Hospital | Claims | The new G codes for drug screenings are denying when billed by outpatient hospitals. | Closed | This issue is resolved. Affected providers can resubmit claims. |  | 2016-11-09
199 | All | Prior Approval | Providers are not receiving the Request for Additional Information or Adverse Decision letters in their secure NCTracks Provider Portal Message Center Inbox. They are receiving them in the US postal mail. | Closed | This issue has been resolved. Going forward, providers should receive the PA letters in their Message Center Inbox. However, the letters generated prior to the issue being resolved will not be posted to the Inbox, since they were already mailed. |  | 2016-07-25
200 | Family Planning | Claims | Claims for MAFDN recipients are being deined when the primary diagnosis is A74.81, Z00.00, Z11.4, Z11.8 and Z01.89. | Closed | This issue has been resolved. Affected providers can resubmit denied claims. |  | 2016-12-20
201 | Professional | Claims | There are services being denied for Edit 2241 - IMMUNIZATION ADMINISTRATION NOT ALLOWED WITHOUT BILLING THE APPROPRIATE IMMUNIZATION CODE when there are immunizations billed on the claim. | Closed | This issue has been resolved. Affected providers can resubmit denied claims. |  | 2016-07-26
202 | Family Planning | Claims | Claims being denied for the DX code B20 with edit 00344 (FAMILY PLANNING INDICATOR NOT IDENTIFIED). | Closed | This issue is resolved. Affected providers can resubmit denied claims. |  | 2016-08-22
203 | Professional | Claims | Childbirth Classes (CPT S9442) were denying for edit 4506/EOB 00082 when billed using ICD-10 code Z32.2 – Encounter for Child Birth Instruction. | Closed | This diagnosis has been added and claims are now processing. Previously denied claims should be submitted for processing. |  | 2016-07-27
204 | Professional | Claims | Providers are being denied for E1399 / W4047 NON-INVASIVE VENT (rental) when an invoice is not attached to the claim or PA | Closed | This issue is resolved. Affected providers can resubmit denied claims. |  | 2016-10-28
205 | All | Enrollment | When an app is open, occasionally the Managing Employee section is reinstating the provider as a Managing Employee and the duplicate cannot be end-dated. | Closed | This issue has been resolved. Exceptions will be dealt with on a case-by-case basis. |  | 2016-08-14
206 | Professional | Claims | Providers are receiving denials with EOB 09951 (TENTH NDC IS NON-COVERED EITHER BY DMA POLICY OR CMS MANDATED) when submitting claims for the following drugs: Coagulation Factor X (Human) lyophilized powder for solution for IV injection (Coagadex), Daratumumab (Darzalex), Sebelipase alfa (Kanuma), Elotuzumab (Empliciti), Talimogene laherparepev (Imlygic), Idarucizumab injection (Praxbind), and Atezolizumab injection. | Closed | This issue has been resolved. Providers should resubmit denied claims. |  | 2016-08-09
207 | All | Enrollment | New providers cannot enroll if their NC Medical Board License Issue Date is after 6/30/2016. The provider license data was loaded with a file from the North Caronia Medical Board with license issue dates equal to or before 6/30/2016, so any licenses issued in July are not present yet. | Closed | This issue has been resolved. |  | 2016-09-21
208 | All | Claims | Definitive Drug Tests are being denied with EOB 58530 (Confirmatory drug testing not allowed in absence of an unanticipated presumptive test), even if a Presumptive Drug Screening has previously been performed. | Closed | This issue has been resolved. Affected providers should resubmit denied claims. |  | 2016-11-23
209 | All | Enrollment | Some providers are experiencing an issue on the "Add Services and Endorsements" page. Providers attempt to complete a new enrollment application (or MCR) and need to add services and endorsements but receives the following error message: You must select as least once service type for taxonomy XXXXXXXXXXX. Regardless if the provider answers Yes or NO to the question, Do you wish to add CAP/DA services, CAP/C services, CAP/Choice services or Innovations Waiver Program, the error still appears and the provider is unable to move forward with the application. | Closed | This issue has been resolved. |  | 2016-10-10
210 | Outpatient, Adult Care Home, and Ambulance | Claims | Claim types outpatient, adultcare home and ambulance are being denied for edit 39850 REGADENOSON MUST BILL WITH CARDIOVASCULAR IMAGING OR STRESS TEST PROCEDURES for the procedure J2785. | Closed | This issue has been resolved. Affected providers can now resubmit denied claims. |  | 2016-12-13
211 | All | Enrollment | Providers are unable to save multiple service locations. NCTracks is not retaining the data and providers are receiving error messages. | Closed | This issue has been resolved |  | 2016-09-26
212 | All | Claims | NCTracks NCCI editing was preventing billing of 77300 with 77295. NCCI editing is updated quarterly and a change to allow both codes will take place with the quarterly updates. | Closed | This issue has been resolved. Affected providers can now bill claims. |  | 2016-09-26
213 | All | Claims | Sterilization claims have denied when billed with ICD 10 code 0UB70ZZ (EXCISION OF BILATERAL FALLOPIAN TUBES, OPEN APPROACH) | Closed | This issue was resolved on September 27, 2016. Affected providers should now resubmit their claims. |  | 2016-09-27
214 | DME | Claims | Diabetic supplies are denying for EOB 1838, 1839, 1840 and 1841 when Medicare HMO is primary. | Closed | This issue has been resolved. Affected providers can resubmit denied claims. |  | 2017-01-23
215 | All | Enrollment | Some providers are receiving an error when creating a Manage Change Request. The error indicates that no Office Administrator has been defined, even though there is an Office Administrator present in either the Ownership section or the Managing Employee/Relationship section of the provider record. | Closed | This issue has been resolved. Affected providers can now submit a Manage Change Request. |  | 2016-11-21
216 | Pharmacy | Claims | Claims for the Flu vaccine submitted by Pharmacies are paying $0 | Closed | This issue has been resolved. Affected pharmacy providers will need to submit a corrected claim. (The claim originally submitted did not deny - it paid zero.) |  | 2016-10-25
217 | PCS and Dental | Claims | Some Personal Care Services (PCS) providers had reported that claims were denying with Explanation of Benefits (EOB) 07023 - TAXONOMY INVALID FOR CLAIM PROVIDER FORM. Upon further investigation,it was learned that dental claims with Taxonomy 1223P0700X were also being denied with EOB 07023. | Closed | This issue has now been resolved for both PCS and dental claims. Affected providers can rebill the denied claims to NCTracks. |  | 2016-11-09
218 | All | Claims | When submitting claims through the NCTracks portal, some providers have reported that the option to add an ordering provider is missing. | Closed | This issue has been resolved. Affected providers can now submit their claims. |  | 2016-11-28
219 | NEMT | Claims | NEMT claims are denying as duplicates against Medicare Crossover claims billed for the same date of service. | Closed | This issue has been resolved. Affected providers can resubmit denied claims. |  | 2017-01-08
220 | DPH | Claims | ITP claims for procedure 97750 are denying for edit 04506/EOB 00082 when billed with ICD-10 diagnosis code. | Closed | All ITP providers that have authorization to bill services for ITP and received a denial for edit 04506 can resubmit claims. Please contact your local CDSA for assistance as needed. |  | 2017-07-06
221 | Dental | Portal | Issue affecting providers trying to obtain Provider Portal inquiries for Dental history on sealants and extractions | Closed | This issue has been resolved |  | 2017-02-20
222 | All | Claims | Claims billed for procedure codes J7312, J3396, J2778, J9035 and J2502 on or after 10/1/2016 are currently being denied for edits 00153/04506 SERVICE IS NOT CONSISTENT WITH/OR NOT COVERED FOR THIS DIAGNOSIS/OR DESCRIPTION DOES NOT MATCH DIAGNOSIS. | Closed | This issue has been resolved. Affected providers can resubmit denied claims. |  | 2017-05-23
223 | All | Claims | It has been reported that some outpatient claims billed for services unrelated to specialized therapy are denying with EOB 57760 (CLAIM DENIED. DUPLICATE OUTPATIENT SPECIALIZED THERAPY SERVICES FOR DOS). | Closed | This issue has been resolved. Affected providers may now resubmit any denied claims . |  | 2017-04-15
224 | All | Claims | It has been reported that CPT 92250 is denying for EOB 0082 for non-covered diagnosis. | Closed | All impacted providers would need to resubmit the denied claims. |  | 2017-06-19
225 | All | Claims | Claims are denying or cut back with Edit 262 when recipient is partially eligible during their inpatient stay. | Closed | This issue has been resolved. All impacted providers should resubmit paid claims as a corrected (replacement) claim for processing. |  | 2017-06-16
226 | All | Claims | Medicare Part A Nursing Home claims are denying for Edit 00010 (REBILL WITH PATIENT LIABILITY AMOUNT AND/OR CORRECT ADMISSION DATE). | Closed | This issue has been resolved. Affected providers can resubmit denied claims. |  | 2017-08-14
227 | All | Claims | Non-covered codes with approved PA through EPSDT or non-covered service indicator are denying with BSG edits. | Closed | This issue has been resolved. Affected providers can resubmit denied claims. |  | 2017-06-26
228 | All | Enrollment | Some people have received an error message when submitting an initial enrollment application for an individual provider. | Closed | This issue has been resolved. |  | 2017-07-30
229 | All | Enrollment | Some providers have received an error message when trying to enter medical license information for April and May 2017. | Closed | This issue has been resolved. |  | 2017-06-27
230 | All | Claims | LTC Pharmacy claims are denying when billing for vaccine products on a professional claim. | Closed | This issue has been resolved. Affected providers can resubmit denied claims. |  | 2017-08-14
231 | All | Enrollment | Providers are receiving an error message when trying to submit a Manage Change Request (MCR). | Closed | This issue has been resolved |  | 2017-10-10
232 | All | Claims | Medicaid secondary claims are failing for EOB 1843 when Medicare denies a line as a non-covered service with the claim adjustment reason PR 49. | Closed | This issue has been resolved. Affected providers may now resubmit any denied claims . |  | 2017-08-28
233 | All | Claims | Providers are currently receiving an error message when using the feature on the secure NCTracks provider portal to "Copy" a previously adjudicated claim that was submitted via the portal. Submission of brand new claims through the portal is not affected. | Closed | This issue has been resolved |  | 2017-07-31
234 | All | AVRS | The Checkwrite functionality on the NCTracks Automated Voice Response System (AVRS) is not currently working. In the meantime, providers can verify checkwrite information using the "Payment History" screen on the secure provider portal. | Closed | This issue has been resolved. |  | 2017-08-02
235 | All | Claims | The original 2nd quarter files had the MUE changed from 2 to 1 for codes 92136 and 76519, and that was changed back to 2 through a “corrected” file. A handful of claims with 2 units billed denied for edit 04520 prior to the fix. | Closed | Providers can resubmit if they billed 2 units for 92136 or 76519 and received an MUE denial in April and June. |  | 2017-07-31
236 | All | Enrollment | If an organization provider goes through a change of ownership (CHOW) but keeps the same NPI, the individual providers that were affiliated with the old organization are not able to affiliate to the new organization because it is viewed as a duplicate. | Closed | This issue has been resolved |  | 2017-09-11
237 | All | Enrollment | Some providers are reporting that their affiliation updates are not visible on the provider record after a MCR (Affiliation MCR or Multiple Changes MCR) is complete and approved. | Closed | This issue has been resolved |  | 2017-09-11
238 | All | Claims | Claims denying for edit 22650/edit 22660 PREVENTIVE MEDICINE & EVALUATION AND MANAGEMENT PROCEDURE CODES NOT ALLOWED SAME DATE OF SERVICE for patient's under the age of 21. | Closed | Affected providers can now resubmit denied claims. |  | 2017-08-28
239 | All | Claims | Procedure code D1354 is pricing incorrectly | Closed | This issue has been resolved. Affected providers can resubmit denied claims. |  | 2017-12-20
240 | All | Claims | Claims being denied for edit 00344 when billed with the diagnosis Z00.01. | Closed | This issue has been resolved. Affected providers can resubmit denied claims. |  | 2017-10-10
241 | All | Claims | Claims are being denied for edit 01843 (MEDICAID DENIED BASED ON CLAIM ADJUSTMENT REASON ASSIGNED BY PRIOR PAYER) when billed with CARC code 109. | Closed | Affected providers can now resubmit denied claims |  | 2017-11-27
242 | All | Claims | Claims are being denied for edit 01843 (MEDICAID DENIED BASED ON CLAIM ADJUSTMENT REASON ASSIGNED BY PRIOR PAYER) when billed with CARC OA 209. | Closed | Affected providers can now resubmit claims. Denied claims should be resubmitted as a new claim. If the claim is in paid status (even if paid $0) a replacement claim will need to be submitted. |  | 2017-11-27
243 | All | Claims | Institutional claims are being denied for MCE edit 03224 (MCE-PROC INCONSISTENT WITH LOS) when billing with the ICD-10 procedure code 5A1955Z. | Closed | Affected providers can now resubmit denied claims |  | 2017-12-04
244 | All | System | Several providers reported an issue with the secure Provider Portal. Providers were able to login to the portal, but when trying to utilize the tabs, such as Claims or Eligibility, the system was slow to respond. | Closed | This issue has been resolved. |  | 2017-12-07
245 | All | Claims | Claims are failing incorrectly for audit 16930 | Closed | (Components denied. Rebill using 92557 as complete procedure versus separate components 92553 and 92556). All affected providers can now resubmit the denied claims. |  | 2017-11-21
246 | All | Claims | There is an issue with pricing of claims when Medicaid is the Tertiary payer. | Closed | The State's decision was to not pursue pricing changes for tertiary claims at this time. |  | 2021-07-02
247 | All | Claims | CRNA claims denied with QZ modifier with AD modifier billed in history for the Anesthesiologist. | Closed | This issue has been resolved. Affected providers can resubmit denied claims. |  | 2018-10-16
248 | All | Claims | Cap case management claims being denied for visit limitation currently being reviewed by the State | Closed | This issue has been resolved. |  | 2020-06-22
249 | All | Claims | Dialysis facility claims currently being denied when billing drug codes J0887 and J0604 | Closed | This issue has been resolved. |  | 2020-06-22
250 | All | Claims | There is an issue with the Non-covered Service Indicator on the portal that is preventing its use for NC Health Choice recipients. Until it can be corrected, claims for items that are over the policy limits will not pay. | Closed | This issue has been resolved. |  | 2018-05-03
251 | All | Prior Approval | Some providers are receiving a lengthy Java/SQL error message when trying to submit a Medicaid prior approval request on the NCTracks provider portal. | Closed | This issue has been resolved. |  | 2018-05-29
252 | All | Claims | Some claims have been inappropriately denying with Edit 00332 - SBHC SPONSORING PROVIDER INELIGIBLE. | Closed | The affected claims were reprocessed in the April 10, 2018 checkwrite. No action is required |  | 2018-04-11
253 | All | Claims | Claim edit 37300 is posting in error for some hospice and encounter claims with dates of service between March 10 and 12, 2018. | Closed | This issue was resolved on 7/8/18. Providers can resubmit affected claims for processing. |  | 2018-07-08
254 | DME | Claims | Edit 00841 (INVALID NDC FOR DIABETIC SUPPLY) is incorrectly posting to DME procedure code A4256. | Closed | The DME A4256 issue was fixed on 6/15/18. Affected providers can now resubmit denied claims. |  | 2018-06-15
255 | Dialysis | Claims | Dialysis claims are denying with edit 02047 (RATE NOT FOUND). | Closed | This issue is resolved. Affected providers can resubmit denied claims. |  | 2018-06-25
256 | All | Claims | Claims are pending in error for edit 44920 (PEND HIGH PAYMENT REVIEW). | Closed | This issue has been resolved. |  | 2018-08-21
257 | All | Claims | DME claims with A9900 are denying due to an NCCI MUE unit limit | Closed | This issue was resolved on 1/7/19. Providers can resubmit affected claims for processing. |  | 2019-01-07
258 | All | Claims | Claims for X-RAY OF KNEE, 1 OR 2 VIEWS (CPT 73560) are denying incorrectly for edit 32740 (REPEAT DIAGNOSTIC PROCEDURE TWICE PER DOS WITH MODIFIERS 76/77) | Closed | This issue has been resolved. |  | 2018-10-10
259 | All | Enrollment | Issue with processing of applications with taxonomy codes 253Z and 251S. The State has been notified and the technical team is researching the issue. | Closed | This issue has been resolved. |  | 2021
260 | All | Enrollment | Some providers are unable to submit their applications. On the managing employee page of the application; the manager’s information is entered, but then disappears when clicking verify address or update. | Closed | The issue has been resolved. |  | 2019-01-31
261 | All | Claims | There is a pricing issue with A4253 when billed with a non Roche NDC (those that require prior approval). | Closed | This issue has been resolved. Affected claims can be resubmitted for proper reimbursement. |  | 2019-02-05
262 | Nursing Home | Claims | Some Nursing Home claims are currently pending for Edit 04525 - BILLING LOCATOR CODE CANNOT BE DERIVED. When NCTracks derives the location code to be used to validate the billing provider address submitted on the claim, the system is checking the admission date for institutional claims , rather than the From date of service. | Closed | This issue has been resolved. |  | 2019-03-07
263 | All | Claims | Claims with 90715 that processed between 10/23/18 – 1/29/19 were subject to 1/lifetime limitation | Closed | Providers should be made aware they can resubmit claims denied during these dates because the issue has now been resolved. |  | 2019-04-10
264 | All | Claims | Claims for CPT A4253 are denying for Edit 04520- CORRECT CODING INITIATIVE MEDICALLY UNLIKELY EDIT | Closed | This issue has been resolved. |  | 2019-04-16
265 | All | Claims/Prior Approval | Edit 03501 Prior Approval cutback applied to line when units are not reached | Closed | This issue has been resolved.
266 | DME Providers | Claims | Claims erroneously denying for edit 01732 | Closed | This issue has been resolved. A bypass was put into place. |  | 2019-10-06
267 | All | Claims | Claims pending for edit 00353 | Closed | This issue has been resolved. |  | 2019-09-04
268 | All | Enrollment | Error message on provider record when 1-2 spaces or multiple names are listed for the first or last name | Closed | This issue is resolved. For some providers, saved drafts may have been deleted when the technical fix went in. |  | 2020-01-16
269 | All | Enrollment | Error message "Find more than one Office Administrators. Please check Ownership page if office administrator is owner of the Organization. Otherwise please check the Agents/Managing Employees page." | Closed | This issue is resolved. |  | 2020-03-17
270 | All | Claims | Procedure code 76830 billed w/FP modifier is denying for members enrolled in the Medicaid health plan for EOB Code: 00024 : MISSING OR INVALID PROCEDURE OR PROCEDURE/MODIFIER COMBINATION. The issue has been escalated to the state for resolution. | Closed | This issue has been resolved.
271 | DME | Claims | Some claims reprocessed for the rate issue related to HCPCS/NDC combination A4253/65702071210 denied unrelated claim lines due to limitation rules. | Closed | This issue has been resolved.
272 | Dental | Claims | The vast majority of the dental claims reprocessed for the rate increase paid appropriately; however, a couple of issues have been identified. Some dental claims reprocessed and denied due to limitation rules, although the claim was paid originally. Some void transactions were not finalized and applied in NCTracks, resulting in some duplicate payments. | Closed | This issue has been resolved. No provider action is required. |  | 2020-04-01
273 | All | Enrollment | Error message "The Requested Affiliation Begin Date precedes the individual providers Begin Date of XX/XX/XXXX" when completing Re-enrollment and MCR applications | Closed | This has been resolved. |  | 2020-01-26
274 | All | Enrollment | Providers are experiencing an issue when adding the taxonomy 251S00000X- Community/Behavioral Health requiring Behavioral Health services license from DHSR. | Closed | This issue has been resolved.
275 | All | Claims | Several claims are denying for Edit: 01931: PROC/NDC XWALK DOES NOT EXIST in error. | Closed | Edit 01931 denials for Outpatient claims and radiopharmaceuticals have been addressed. Claims related to these issues can be resubmitted. |  | 2020-05-14
276 | All | Claims | Outpatient Specialized Therapy claims billed with POS 02 are currently denying for Edit: 00148: INVALID PLACE OF SERVICE FOR PROCEDURE OR REVENUE CODE. | Closed | This issue has been resolved. Providers should refer to https://files.nc.gov/ncdma/covid-19/NCMedicaid-Telehealth-Billing-Code-Summary.pdf on the DHB website.
277 | Hospital/NF | Claims | Institutional claims with condition code DR denied with edit 1203/EOB 1803 | Closed | This issue has been resolved. Condition code DR is now acceptable in NCTracks. Providers can resubmit denied claims. |  | 2020-05-07
278 | All | Enrollment | There is an issue with receiving Public Consultant Group (PCG) results in NCTracks | Closed | This has been resolved. |  | 2020-07-20
279 | All | Enrollment | Office administrators (OAs) have received the notification indicating that they have applications that need to be reviewed and approved; however, when the OA logs in to review them, there are none visible. Some OAs are also being prompted to assign the application to an OA. | Closed | This issue has been resolved. |  | 2020-12-07
280 | All | Claims | Some claims reprocessed for the temporary 5% rate increase detailed in SPECIAL BULLETIN COVID-19 #99 (posted June 15, 2020) have paid an amount different than the expected 5% increase. | Closed | This issue has been resolved. Impacted claims were reprocessed on 12/7/2021. |  | 2021-12-07
281 | All | Enrollment | Providers are receiving “The ZIP Code you entered could not be found. Please check your entry and try again.” when completing a manage change request. The check box for attesting to the address is missing. | Closed | This issue has been resolved. |  | 2020-12-22
282 | All | Claims | Claims billed with modifier CR are failing for edit 02104: PROVIDER TAXONOMY NOT ALLOWED FOR MODIFIER SUBMITTED. | Closed | This issue has been resolved. |  | 2021-02-05
283 | All | Claims | An issue affecting some providers’/Trading Partners’ Remittance Advice (RA) Statements involving a double pound sign (##) being automatically placed into the modifier field for procedure codes without a modifier has been identified. This has prevented RAs from automatically posting. | Closed | This issues has been resolved.
284 | All | Enrollment | Phone number not updating on Manage Change Request upon application approval. | Closed | This issue has been resolved. |  | 1905-07-13
285 | All | Enrollment | Optional Board Certifications not updating on Manage Change Request that do not require credentialing | Closed | This issue has been resolved. |  | 2021
286 | All | Claims | An issue affecting some clearing houses that did not receiving 835's for their customers. | Closed | This issues has been resolved.
287 | Institutional | Claims | Vaccine administration codes billed on an institutional claim with revenue code 0771 are not reimbursing published fee schedule rate of $40. | Closed | Providers should follow guidance in Special Bulletin COVID-19 #243.
288 | All | Enrollment | Bed Accommodation Error Message when trying to submit an Manage Change Request (MCR). | Closed | This issues has been resolved. |  | 2021-08-08
289 | All | Enrollment | Users trying to remove the Resident Training License (RTL) taxonomy and the system is not allowing because it is currently in a Suspended status. The workaround for this issue is, to update the RTL taxonomy with either an end dated or make it active with a future end date, so that the provider can submit the application. | Closed | This issue has been resolved. |  | 2021
290 | All | Claims | Pregnancy Medical Home (PMH) program ended June 30, 2021. Some claims for providers who were PMH providers are pending with edit 353/EOB 01660 NO RATE ON FILE. Related DHB notices - https://medicaid.ncdhhs.gov/media/9833/open and https://medicaid.ncdhhs.gov/providers/fee-schedules/pregnancy-medical-home-fee-schedules. | Closed | Claims pended for EOB 01660 have been released for adjudication.
291 | Home Health | Claims | Home Health claims for A4450 and A4452 were denied for : 00431 PROCEDURE CODE IS NOT COVERED BY THE ASSIGNED BSG FOR THE DATES OF SERVICE. | Closed | This issue has been resolved. Providers can resubmit previously denied claims.
292 | All | Enrollment | Some providers are receiving an error message (An error occurred while submitting your enrollment application. Please contact help desk 800-688-6696.) when trying to submit an initial enrollment application, re-enrollment application, or manage change request (MCR). This issue occurs when a user adds a managing employee, then edit it again. If user want to submit now, please delete the added MR(s) and submit application. | Closed | This issue has been resolved. |  | 2022-01-11
293 | All | Claims | Some provider Children's Developmental Services Agency (CDSA) claims are being deined due to an issue with Carve Out rules added after the Managed Care Launch. | Closed | Claims impacted were reprocessed on 5/10/2022 checkwrite.
294 | Institutional | Claims | There is a known billing issue with the vaccine administration codes and outpatient dialysis facilities. This issue is only related to non COVID-19 vaccine administration codes. | Closed | This issue has been resolved. Claims processed appropriately.
295 | All | Enrollment | Some providers are not able to select the Pay Now link after submission. Pay Now link is greyed out. | Closed | This issue has been resolved. |  | 2023-08-01
296 | All | Re-verification | Some providers are not receiving confirmation email for payment. | Closed | System issue was resolved and affected providers have received confirmation emails as of 9/5/2023. |  | 2023-09-05
297 | Board Certified Behavior Analyst | Enrollment | The North Carolina Behavior Licensure Board is now authorizing licenses, but NC Medicaid enrollment is not yet available. Last Update was 4/20/23. | Closed | As of 9/12/23, Board Certified Behavior Analysts are able to be enrolled. |  | 2023-09-12
298 | All | Enrollment | Providers are receiving the following error message on the Accreditation Page during their Re-enrollment, Re-verification, or Manage Change Request (MCR) applications: "Effective date for required accreditation/certification/licensure must be equal to or before the taxonomy begin date." | Closed | This issue was resolved on 10/22/23. A fix was deployed and this issue no longer exists for active taxonomy codes. |  | 2023-10-22
299 | All | Ennrollment | An issue has been identified that is preventing providers from back-dating applications. | Closed | This issue has been resolved. Providers can now back-date applications. |  | 2023-09-24
300 | Physicians | Claims | Counseling code 99401 denying since 5/12/23 | Closed | This issue has been resolved. Providers can resubmit previously denied claims. |  | 2023-12-01
301 | Physicians, Nutritionists, Dietitians | Claims | CPT Codes 97802 and 97803 denying for EOB 02310 and EOB 02037 | Closed | This issue has been resolved. Claims impacted will be reprocessed, date to be posted in a future communication. |  | 2024-01-31
302 | Professional Services | Claims | For 87661 with FP modifier under MAFDN BSG does not list POS 11 as covered but Clinical Policy 1E-7 Family Planning Services does list POS 11 as covered for the procedure codes in this policy. | Closed | This issue has been resolved. Providers can resubmit previously denied claims. |  | 2024-02-21
303 | DME Providers | Claims | The pricing on A4670 was end dated in NCTracks as of 09/30/2023. However, Clinical Policy 5A-3 Nursing Equipment and Supplies lists this code as active and valid. Claims are denying in NCTracks for A4670 because all pricing has been end dated. | Closed | This issue has been resolved. Providers can resubmit previously denied claims. |  | 2024-01-24
304 | Professional Services | Claims | Providers are receiving claim denials when they bill with EP modifier for procedure code 90480. | Closed | This issue has been resolved on 1/31/2024. Providers can resubmit previously denied claims. |  | 2024-01-31
305 | Institutional, Inpatient | Claims | Revenue code 0161 is being denied in NCTracks for 00432 REVENUE CODE IS NOT ON PROCEDURE UNIVERSAL TABLE FOR DATES OF SERVICE, EOB code 02311. | Closed | This issue has been resolved. Providers can resubmit previously denied claims. |  | 2024-04-10
306 | Professional | Claims | ASC Dental surgical code G0330 pricing issue. | Closed | This issue has been resolved. |  | 2024-01-01
307 | Professional | Claims | Additional birth codes are being denied for edit 49270 NCCI Edit | Closed | This issue has been resolved. Providers should review CCP 1E-5 and resubmit claims as applicable. |  | 2024-06-15
308 | Professional | Claims | There is a known billing issue when CPT codes: 95885, 95886, 95905, 95907, 95908, 95909, 95910, 95911, 95912, and 95913 are denied with EOB 00024 & 02310. | Closed | This issue has been resolved. |  | 2024-03-20
309 | All | Enrollment | For re-enrollment applications only, the SSN of the OA is not pre-populated on the Indiv/Org Basic Information Page. If SSN is entered, the application can be submitted with no issues. | Closed | This issue has been resolved. |  | 2024-04-10
310 | DME | Claims | Claims for the taxonomies list below are being denied when a procedure code is billed with the required NU modifier for edit 02104 “PROVIDER TAXONOMY NOT ALLOWED FOR MODIFIER SUBMITTED”: 213E00000X Podiatrist, 213EP1101X Primary Podiatric Medicine 213ES0103X Foot & Ankle Surgery 213ES0131X Foot Surgery | Closed | This issue has been resolved. Impacted claims were partially reprocessed on 5/14/2024. The remaining claims will be reprocessed on 7/16/2024. |  | 2024-05-14
311 | Professional Services | Claims | Podiatry claims are being denied for EOB Code 01647 (THE PRIMARY OR SECONDARY DIAGNOSIS CODE BILLED DOES NOT MEET THE MEDICAID BILLING REQUIREMENTS FOR THIS PROVIDER TAXONOMY QUALIFIER). | Closed | This issue has been resolved. Providers can resubmit previously denied claims. |  | 2024-12-06
312 | All | Enrollment | An error is preventing providers with a status of "terminated" from submitting a Change OA Application. | Closed | This issue has been resolved. |  | 2024-04-12
313 | All | Enrollment | Providers are receiving an error when attempting to submit/begin a back-dated MCR application. | Closed | This issue has been resolved |  | 2024-04-21
314 | Physicians | Claims | Counseling code 99401, modifier 25 and NCCI denial | Closed | This issue has been resolved. Providers can resubmit previously denied claims. |  | 2024-04-24
315 | All | Claims | Claims for MAFDN plans are being denied for not having a qualifying primary diagnosis code under edit 02604 when using certain diagnosis codes found in policy 1E-7. | Closed | This issue has been resolved. Providers can resubmit previously denied claims. |  | 2024-07-23
316 | All | Enrollment | Users are receiving error message "Server Error in '/DirectConnect' Application, when trying to add a new user under New User Setup. | Closed | This issue has been resolved. |  | 2024-06-09
317 | Professional | Claims | Claims billed with HCPCS code G0330 pending with EOB 44920. | Closed | This issue has been resolved. Claims pending have been released. Providers should review RA for updates. |  | 2024-05-08
318 | Professional | Claims | Claims billed with diagnosis code Z13.31 denying claim lines with EOB 01610 - FAMILY PLANNING PROCEDURE CODE REQUIRES FAMILY PLANNING DIAGNOSIS. PLEASE CORRECT AND RESUBMIT. | Closed | This issue has been resolved. Providers can resubmit previously denied claims. |  | 2024-06-17
319 | All | Enrollment | The Submitted Applications section of the Status Management Page is intermittently loading with no data. This can prevent a provider for uploading supporting documentation or paying a fee related to the submitted application. | Closed | This issue has been resolved. The Submitted Applications section of the Status Management Page is intermittently loading correctly. |  | 2024-07-03
320 | Professional | Claims | FQHC/LHD claims billed with CPT code 90651 are denying claim lines with EOB 01660 - NO RATE ON FILE | Closed | This issue has been resolved. Providers can resubmit previously denied claims. |  | 2024-07-05
321 | Professional | Claims | The MPW plan currently requires prior approval for optical codes 92015, S0620, and S0621. However, these codes should not require prior approval. | Closed | All claims have been reprocessed for this issue. |  | 2024-07-03
322 | Professional | Claims | CAP claims denying for other insurance EOB 00094. | Closed | This issue has been resolved. Providers can resubmit claims. |  | 2024-07-17
323 | All | Claims | Office administrators (Oas) are unable to view recently approved providers on the Status Management page. | Closed | This issue has been resolved. Oas are now able to view recently approved providers on the Status Management Page. |  | 2024-08-26
324 | Professional | Claims | Claims filed with CPT code 99078 with TH modifier denied for EOB 07702. | Closed | This issue has been resolved. Providers can resubmit previously denied claims. |  | 2024-07-23
325 | Institutional | Claims | Inpatient claims paying incorrectly when admit and discharge are same day. Per Clinical Coverage Policy 2A-1, Attachment B, Section A #14: Services for beneficiaries who are admitted and discharged on the same day, either to home or to a non–acute care facility, shall be billed as outpatient services. | Closed | The issue has been resolved. Claims now deny per policy. See EOB message instruction for claim resolution. |  | 2024-09-15
326 | All | Enrollment | Applications in which the provider paid the enrollment fee on 9/11/24 are in "Pending" status. | Closed | The issue has been resolved. Applications that were stuck in "Pending" status have progressed forward. |  | 2024-09-25
327 | Professional | Claims | EOB 00708 ADMISSION HISTORY AND PHYSICAL ALLOWED ONCE PER HOSPITALIZATION. TRANSFERS WITHIN THE SAME FACILITY DO NOT SUPPORT THE BILLING OF ADMISSION. REBILL APPROPRIATE LEVEL CPT E/M CODE may be posting on claims inappropriately. | Open | The State is aware of this issue and are currently working towards a solution.
328 | Physicians | Claims | Edit 02241 posting when immunization admin code billed with Vaccine code 90677 and 90671. | Closed | his issue has been resolved. Providers can resubmit previously denied claims. |  | 2024-12-30
329 | Professional | Claims | Medicaid secondary claims are failing for EOB 1843 when Medicare denies a line as a non-covered service with the claim adjustment reason PR 49. | Closed | This issue has been resolved. Providers can resubmit previously denied claims. |  | 2025-01-06
330 | DME | Prior Approval | There is a known issue with some DME procedure codes that require Prior Approval (PA) and the PA transitioning from the Health Plan to Medicaid Direct being rejected. This may result in claims denying for PA. | Closed | Providers do not need to request a new PA. The State and GDIT are aware of the PA rejection issue and are working towards a solution. |  | 2025-06-16
331 | Professional | Claims | Claims filed with CPT code 92523 and modifiers 52 for LEA (Local Education Agency) are denying in error. | Closed | This issue has been resolved. Providers can resubmit impacted claims. A systematic reprocessing is being considered and future communication will be shared on this effort. |  | 3/19/2025
332 | All | Enrollment | Starting 2/9, providers with owners with commas in the name are unable to move past the Ownership Page and submit a MCR. | Closed | This issue has been resolved. |  | 2025-03-09
333 | Professional | Prior Approval | Visual aid PA entry issue on detail service line when selecting checkbox for "Rendering provider is the same as the billing provider”. The portal does not automatically populate in the Rendering Provider field. | Closed | This issue has been resolved. Providers can access PA entry as normal. |  | 2025-03-17
334 | All | Claims | Claims denying with EOB 00531 SERVICES INCLUDED IN MONTHLY PROFESSIONAL DIALYSIS FEE for codes that are unrelated to dialysis. | Closed | This issue has been resolved. Providers may resubmit impacted claims. |  | 2025-05-20
335 | All | Claims | Edit 01790 -MAX SUBMITTED UNITS FOR REVENUE CODES FOR OUTPATIENT SPECIALIZED THERAPY IS ONE is being applied to Medicare Part C claims for revenue code 0420 but according to the edit, these line items should have been bypassed. | Closed | This issue has been resolved. Providers may resubmit impacted claims. |  | 2025-03-31
336 | Family Planning | Claims | Procedure code 90651 with modifier FP is denying with EOB 01660 NO RATE ON FILE. | Closed | This issue has been resolved. Providers may resubmit impacted claims. |  | 2025-04-08
337 | Dental | Claims | Claims are denying with EOB 01831 for dental orthodontic maintenance codes D8670 and D8680 when the member has become Medicare enrolled. | Closed | This issue has been resolved. Providers may resubmit impacted claims. |  | 2025-09-12
338 | Hospice | Claims | When a beneficiary has a primary insurance, hospice room and board claims are denying for EOB 00094 AN INSURANCE PRIMARY TO MEDICAID IS SUSPECTED. PLEASE RESUBMIT WITH PRIMARY INSURANCE INFORMATION DOCUMENTED ON THE MEDICAID CLAIM. | Closed | This issue has been resolved. Providers may resubmit impacted claims. |  | 2025-06-15
339 | Professional | Claims | Personal Care Service (PCS) Adult Care Home (ACH) claims billed with CPT code 99509 and modifiers HC, TT, SC, HH, HI & HQ are receiving overpayments due to the per diem rate changes that went into effect with DOS 4/1/2025. | Closed | This issue has been resolved. |  | 2025-05-13
340 | All | Enrollment | Providers are unable to submit MCR applications to terminate health plans. They receive an error message. | Closed | This issue has been resolved. |  | 2025-05-25
341 | All | Claims | Providers are seeing pending and denied claims for services requesting ordering and referring provider. | Closed | This issue has been resolved. Providers can refer to the Medicaid Bulletin, Dec. 12, 2024 for claim requirements. Federal Regulation Guidelines for Ordering, Prescribing, or Referring Providers. https://medicaid.ncdhhs.gov/blog/2024/12/12/federal-regulation-guidelines-ordering-prescribing-or-referring-providers |  | 2025-06-10
342 | CAP | Claims | Providers billing for services for CAP beneficiaries are experiencing claim denials when the ordering and referring provider NPIs are missing. This issue began on 6/15/25 and a provider announcement was published on 6/20/25. | Closed | A temporary relief measure for CAP claims denied with no ordering and/or referring provider since 6/15/25 has been implemented. Providers can now resubmit denied claims and submit new claims for all service dates without the ordering and referring provider NPIs. Previously denied claims will be reprocessed on 07/15/2025. Dates and details on when the edits will be set back to deny will also be in a future announcement. During this period of relief, providers should be working towards including this required provider information on claims. |  | 2025-07-16
343 | Chiropractors | Claims | Providers received denials with EOB 00082 SERVICE IS NOT CONSISTENT WITH/OR NOT COVERED FOR THIS DIAGNOSIS/OR DESCRIPTION DOES NOT MATCH DIAGNOSIS when billing codes 98940, 98941 or 98942. | Closed | This issue has been resolved. Providers may resubmit previously denied claims with service dates August 1, 2024 to August 8, 2025. |  | 2025-08-19
344 | Professional | Claims | Claims posting edit 00353 No Rate on File on some patient visit codes | Closed | This issue has been reviewed and determined to be resolved with no action required. |  | 2025-10-28
345 | Professional | Claims | Claims posting audit 60660 for HCPCS code A4332 | Closed | This issue has been resolved. Providers can resubmit previously denied claims. |  | 2025-11-19
346 | DME | Claims | NCTracks is aware of an issue when billing E0600 and B9002 regarding payment. | Closed | This issue has been resolved and providers can now resubmit corrected/replacement claims for any DME Rental item paid $0 effective with dates 10/1/2025 |  | 2025-12-12
347 | DME | Claims | Issue has been identified with claim reimbursements for A4253, A4256, A4258 and A4259 effective 10/1/2025. | Closed | This issue has been resolved. Providers may resubmit previously denied claims or await future system reprocessing. |  | 2026-02-13
348 | CAP/DA & CAP/CD | System | Edit 60980 – CAPDA/CD Dollar Limit for Waiver Goods & Services applies calendar year limits, but policy uses fiscal year, causing claim discrepancies | Open | The State is aware of this issue and are currently working towards a solution.
349 | Professional | Claims | Claims with procedure code 92250 and 92025 are denying with EOB 00082 SERVICE IS NOT CONSISTENT WITH/OR NOT COVERED FOR THIS DIAGNOSIS/OR DESCRIPTION DOES NOT MATCH DIAGNOSIS. | Closed | This issue has been resolved. Providers may resubmit previously denied claims or await system reprocessing scheduled for the 3/17/2026 check write. |  | 2026-01-07
350 | Professional | Claims | Some claims with procedure code J0585 are denying with EOB 00082 SERVICE IS NOT CONSISTENT WITH/OR NOT COVERED FOR THIS DIAGNOSIS/OR DESCRIPTION DOES NOT MATCH DIAGNOSIS. | Closed | This issue has been resolved. Providers can resubmit previously denied claims. |  | 2026-01-23
351 | All | Claims | Claim or claim lines with primary insurance CARC 147 were set to deny with EOB MEDICAID DENIED BASED ON CLAIM ADJUSTMENT REASON ASSIGNED BY PRIOR PAYER. This has been adjusted to no longer deny. | Closed | This issue has been resolved. Providers can resubmit previously denied claims. |  | 2026-01-30
352 | Professional | Claims | Claims with procedure code 98981 are posting EOB 01610 FAMILY PLANNING PROCEDURE CODE REQUIRES FAMILY PLANNING DIAGNOSIS. PLEASE CORRECT AND RESUBMIT. | Closed | This issue has been resolved. Providers can resubmit previously denied claims. | Open | 2026-03-24
353 | Outpatient | Claims | Claims with procedure codes 0202U, 0223U, or 0224U are posting EOB 00158 THIS REVENUE CODE REQUIRES A CPT LABORATORY PROCEDURE C | Closed | This issue has been resolved. Providers can resubmit previously denied claims. | Open | 2026-04-30
354 | Professional | Claims | Claims with procedure code 90623 and 90678 are posting EOB 01422 IMMUNIZATION ADMINISTRATION NOT ALLOWED WITHOUT BILLING THE APPROPRIATE IMMUNIZATION CODE. REFER TO THE LATEST HEALTH CHECK BILLING GUIDE | Closed | This issue has been resolved. Providers can resubmit previously denied claims. |  | 2026-03-23
355 | Professional | Claims | Claims posting EOB 01660 NO RATE ON FILE for some codes that are to be priced off invoice per PADP fee schedule. | Closed | This issue has been resolved. Providers can resubmit previously denied claims. |  | 2026-04-09
356 | Dialysis Facility | Claims | Dialysis facility claims with J3373 denying with EOB 01177. | Closed | This issue has been resolved. Providers can resubmit previously denied claims. |  | 2026-05-06
357 | Outpatient Specialist Therapy | Claims | Claims with new 2026 procedure codes 92628, 92629, 92631, 92632, 92634, 92635, 92636, 92637, 92638, 92639, 92641 & 92642 are denying when billed by an Audiologist. | Open | The State is aware of this issue and are currently working towards a solution.
358 | Physician | Claims | Claims with procedure codes 99492, 99393, 99494, and G2214 are denying with EOB 00036 Invalid Place of Service and 02313 Invalid Rendering Provider Taxonomy. | Open | The State is aware of this issue and are currently working towards a solution.
359 | Dental | Claims | Dental providers are receiving EOB 00010 DIAGNOSIS OR SERVICE INVALID FOR RECIPIENT AGE. VERIFY MID, DIAGNOSIS, PROCEDURE CODE OR PROCEDURE CODE/MODIFIER COMBINATION FOR ERRORS. CORRECT AND SUBMIT AS A NEW CLAIM when billing D1354 for recipients over 5 years old. | Open | The State is aware and is working towards a resolution.
360 | All | Enrollment | Error Message: Find more than one Office administrators. Please check Ownership page if office administrator is owner of the organization. Otherwise please check the Agents/Managing Employees page. | Open | The State is aware and is working towards a resolution.
361 | All | Enrollment | Error Message: You are already the Office Administrator for NPI: #. You do not need to submit an OA change application for this provider. OA does not have access in Status and Managemetn screen and/or user is the current OA but when completing applications such as an MCR or re-enrollment, the NCID is not shwoing on the application. | Open | The State is aware and is working towards a resolution.
362 | All | Enrollment | Affiliation tab is not allowing affiliation to be selected or date entered therefore producing an error message. | Open | The State is aware and is working towards a resolution.
363 | Professional | Claims | LEA (Local Education Agency) claims posting edits 02438 & 02440 which requires an ordering and referring provider on the claim. This requirement was set to go into effect for claims with “Dates of Service” 7/1/2026 and forward. However, claims have denied that were processed on 7/1/2026 with a DOS prior to 7/1/2026. | Open | The State is aware of this issue and are currently working towards a solution.